## First Aid Information System – Work Breakdown Structure (WBS)

### Level 1: 1.0 First Aid Information System

### Level 2: Major Phases

1.1 System Analysis & Planning
1.2 System Design
1.3 System Development
1.4 System Testing & Validation
1.5 Deployment & Documentation
1.6 Project Closure

### Level 3: Tasks under Each Phase

#### 1.1 System Analysis & Planning

- 1.1.1 Gather requirements (first aid topics, content types)

- 1.1.2 Identify hardware and software needs

- 1.1.3 Define database schema (SQLite)

- 1.1.4 Create project schedule and assign tasks

#### 1.2 System Design

- 1.2.1 Design user interface and user experience (UI/UX)

- 1.2.2 Design database tables and relationships

- 1.2.3 Prepare prototypes

- 1.2.4 Review and approval of design

#### 1.3 System Development

- 1.3.1 Frontend development using Flutter

- 1.3.2 Backend development using SQLite

- 1.3.3 Integrate text, images, and videos

- 1.3.4 Implement offline access feature

#### 1.4 System Testing & Validation

- 1.4.1 Unit testing (individual functions)

- 1.4.2 Integration testing (Flutter + SQLite)

- 1.4.3 User acceptance testing (Ministry of Health approval)

- 1.4.4 Bug fixing and optimization

#### 1.5 Deployment & Documentation

- 1.5.1 Deploy app to Android and iOS platforms

- 1.5.2 Conduct user training.

- 1.5.3 Prepare user manuals and technical documentation

#### 1. 6 Project Closure

- 1.6.1 Final review meeting and approval

- 1.6.2 Submit final report and documentation

- 1.6.3 Handover to Ministry of Health

WBS DICTIONARY

| Code | Task Description | Assigned People | No. of Resources | Budget (LE) | Milestone (Date) |
| --- | --- | --- | --- | --- | --- |
| 1.1.1 | Gather requirements (first aid topics, content types) | Ahmed Nasser (Analyst), Sarah Fathy (Researcher) | 2 | 1,500 | 05/03/2026 |
| 1.1.2 | Identify hardware and software needs | Omar Khaled (System Analyst) | 1 | 500 | 10/03/2026 |
| 1.1.3 | Define database schema (SQLite) | Mariam Said (DB Designer) | 1 | 800 | 10/03/2026 |
| 1.1.4 | Create a project schedule and assign tasks | Laila Mostafa (Project Manager) | 1 | 700 | 15/03/2026 |
| 1.2.1 | Design UI/UX | Hossam Magdy (UI/UX Designer), Jana Ali (Graphic Assistant) | 2 | 1,200 | 25/03/2026 |
| 1.2.2 | Design database tables and relationships | Mariam Said (DB Designer) | 1 | 700 | 25/03/2026 |
| 1.2.3 | Prepare prototypes | Jana Ali (Designer), Youssef Kamal (Frontend Dev) | 2 | 1,000 | 5/04/2026 |
| 1.2.4 | Review and approve design | Laila Mostafa (PM), Ahmed Nasser (Analyst) | 2 | 500 | 5/04/2026 |
| 1.3.1 | Frontend development using Flutter | Youssef Kamal, Reem Tamer (Developers) | 2 | 2,500 | 20/04/2026 |
| 1.3.2 | Backend development using SQLite | Mariam Said (DB Dev), Ali Hassan (Backend Dev) | 2 | 2,000 | 25/04/2026 |
| 1.3.3 | Integrate text, images, and videos | Reem Tamer, Jana Ali | 2 | 1,000 | 5/05/2026 |
| 1.3.4 | Implement offline access feature | Ali Hassan (Backend Dev) | 1 | 800 | 5/05/2026 |
| 1.4.1 | Unit testing (individual functions) | Rania Fathy (Tester), Ahmed Salah (QA Engineer) | 2 | 1,000 | 20/05/2026 |
| 1.4.2 | Integration testing (Flutter + SQLite) | Ahmed Salah (QA), Youssef Kamal (Dev) | 2 | 800 | 30/05/2026 |
| 1.4.3 | User acceptance testing | Ministry of Health team (3 reviewers) | 3 | 700 | 5/06/2026 |
| 1.4.4 | Bug fixing and optimization | Developers team | 2 | 1,000 | 15/06/2026 |
| 1.5.1 | Deploy app to Android and iOS | Ali Hassan (Dev), Laila Mostafa (PM) | 2 | 1,200 | 25/06/2026 |
| 1.5.2 | Conduct user training | Sarah Fathy (Trainer) | 1 | 600 | 5/07/2026 |
| 1.5.3 | Prepare user manuals and technical documentation | Mariam Said (Tech Writer), Jana Ali (Designer) | 2 | 1,000 | 10/07/2026 |
| 1.6.1 | Final review meeting and approval | Laila Mostafa (PM), Ministry of Health Rep. | 2 | 500 | 15/07/2026 |
| 1.6.2 | Submit final report and documentation | PM + Team | 3 | 400 | 20/07/2026 |
| 1.6.3 | Handover to Ministry of Health | PM + IT Admin | 2 | 600 | 25/7/2026 |

## Responsibility Matrix

| WBS Code & Task | Laila (PM) | Ahmed (Analyst) | Sarah (Researcher) | Omar (System Analyst) | Mariam (DB Dev) | Hossam (UI/UX) | Jana (Designer) | Youssef (Frontend) | Ali (Backend) | Reem (Mobile) | Ahmed S. (QA) | Rania (Tester) | MOH Team |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
| Gather requirements | S | R | R | S | – | – | – | – | – | – | – | – | – |
| Identify hardware & software needs | S | R | – | R | – | – | – | – | – | – | – | – | – |
| Define database schema (SQLite) | – | S | – | S | R | – | – | – | – | – | – | – | – |
| Create project schedule & assign tasks | R | S | – | – | – | – | – | – | – | – | – | – | – |
| Design UI/UX | S | – | – | – | – | R | S | – | – | – | – | – | – |
| Design database tables & relationships | – | – | – | S | R | – | – | – | – | – | – | – | – |
| Prepare prototypes | – | – | – | – | – | R | R | S | – | – | – | – | – |
| Review & approval of design | R | S | – | – | S | – | – | – | – | – | – | – | – |
| Frontend development (Flutter) | S | – | – | – | – | S | – | R | – | S | – | – | – |
| Backend development (SQLite) | – | – | – | – | R | – | – | – | R | – | – | – | – |
| Integrate text, images, and videos | – | – | – | – | S | S | R | R | – | S | – | – | – |
| Implement offline access feature | – | – | – | – | S | – | – | – | R | – | – | – | – |
| Unit testing (individual functions) | – | – | – | – | – | – | – | S | S | S | R | R | – |
| Integration testing (Flutter + SQLite) | – | – | – | – | S | – | – | S | S | – | R | R | – |
| User acceptance testing (MOH approval) | S | – | – | – | – | – | – | – | – | – | S | – | R |
| Bug fixing & optimization | – | – | – | – | S | – | – | R | R | S | S | – | – |
| Deploy app (Android/iOS) | R | – | – | – | S | – | – | S | R | S | – | – | – |
| Conduct user training | S | – | R | – | – | – | – | – | – | – | – | – | S |
| Prepare manuals & documentation | S | – | – | – | R | – | R | – | – | – | – | – | – |
| Final review & approval meeting | R | S | – | – | – | – | – | – | – | – | – | – | R |
| Submit final report & documentation | R | S | – | – | S | – | – | – | – | – | – | – | – |
| Handover to Ministry of Health | R | – | – | – | – | – | – |  |  |  |  |  |  |